[YOUR ORGANISATION NAME]

ABN: [YOUR ABN]  |  NDIS Provider Number: [YOUR PROVIDER NUMBER]

| Document Title: | SIL Registration Step-by-Step Walkthrough Guide |
| --- | --- |
| Document Number: | DOC-64 |
| Version: | 26.04 |
| Date Created: | [INSERT DATE] |
| Last Reviewed: | April 2026 |
| Next Review Due: | [INSERT DATE — within 12 months] |
| Approved By: | [INSERT NAME AND POSITION] |
| Owner: | [Nominated Manager / Director] |
| NDIS Practice Standard: | Core Module — Registration Process |
| Applicable To: | All workers, contractors, and volunteers |

## Your SIL Registration Roadmap

This guide walks you through the complete process of registering as a SIL provider with the NDIS Quality and Safeguards Commission. Estimated timeline: 3–6 months from start to registration certificate.

## Step 1: Prepare Your Documentation (Weeks 1–4)

- Customise all policy documents in this SIL Rescue Kit with your organisation’s name, ABN, and provider details

- Complete the Organisational Chart showing your governance structure

- Complete Key Personnel Suitability Assessments for all key personnel

- Ensure all workers have current NDIS Worker Screening Checks (populate the Worker Screening Register)

- Set up your operational registers: Incident Register, Complaints Register, Continuous Improvement Register, Risk Register, Document Control Register

- Prepare participant files: support plans, service agreements, consent forms

- Conduct your first internal audit using the Internal Audit Report Template

- Review the Audit Evidence Checklist to confirm you have everything

## Step 2: Submit Your Application (Week 5)

- Go to the NDIS Commission Applications Portal: www.ndiscommission.gov.au/apply

- Create an account and log in

- Select your registration groups — for SIL, select Registration Group 0115: Assistance with Daily Life Tasks in a Group or Shared Living Arrangement

- Also select any other registration groups you intend to deliver (e.g., community participation, personal activities)

- Complete the self-assessment questions for each selected module

- Upload supporting documents as requested

- Submit your application

Tip: The Commission may take several weeks to process your application and conduct suitability assessments for key personnel.

## Step 3: Engage an Approved Quality Auditor (Week 5–6)

- Find an Approved Quality Auditor (AQA) from the NDIS Commission’s list or the JAS-ANZ website

- Request quotes from at least 2–3 auditors — prices vary significantly

- Confirm the auditor can conduct a CERTIFICATION audit (not verification — SIL requires certification)

- Book your audit date — note that auditors are booking 8–12+ weeks out due to the SIL registration deadline

- Provide the auditor with your document set and evidence package

## Step 4: Stage 1 Audit — Document Review (Weeks 8–10)

The auditor reviews your documentation remotely. They will:

- Review all policies, procedures, and registers against the NDIS Practice Standards

- Assess your self-assessment responses

- Request clarification or additional documents if needed

- Provide a Stage 1 report identifying any gaps or concerns to address before Stage 2

## Step 5: Address Stage 1 Findings (Weeks 10–12)

If the auditor identifies gaps:

- Address them before the Stage 2 site visit

- Provide updated documentation to the auditor

- This is your opportunity to fix issues — take it seriously

## Step 6: Stage 2 Audit — Site Visit (Weeks 12–14)

The auditor visits your SIL site(s) and head office. They will:

- Interview key personnel (Director, Operations Manager, Quality Lead)

- Interview frontline support workers

- Interview participants receiving SIL supports (with consent)

- Observe service delivery

- Review participant files, staff files, and operational records

- Assess whether your policies are actually implemented in practice

Tip: Brief your team beforehand. Conduct mock interviews. Ensure everyone knows where to find policies and how to explain their role in incident reporting, complaints, and participant rights.

## Step 7: Audit Report and Registration Decision (Weeks 14–20)

After the audit:

- The auditor submits their report to the NDIS Commission within 28 days

- If non-conformances are identified, you have 3 months (major) or 18 months (minor) to address them

- The Commission reviews the report and makes a registration decision

- If approved, you receive your Certificate of Registration — valid for 3 years

- Your mid-term audit will be due approximately 18 months after registration

## Key Tips for Success

- Start early — the process takes 3–6 months minimum

- Don’t just have policies — IMPLEMENT them. Auditors check for evidence of use, not just documents

- Populate your registers with real entries before your audit (incidents, complaints, improvements, risks)

- Brief your team — workers who can’t explain your policies raise red flags for auditors

- Date and version-control every document — undated documents are the #1 audit failure

- Get multiple auditor quotes — the cheapest isn’t always the best, but don’t overpay either

CONFIDENTIAL — This document is the property of [YOUR ORGANISATION NAME]. Unauthorised reproduction or distribution is prohibited.

Document: SIL Registration Step-by-Step Walkthrough Guide | Generated by NDISCompliant (ndiscompliant.com.au)